## Gantt Chart Template
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | RECESS WEEK |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Weekly Meeting - to share ideas and update progress (4 p.m.) | All | - | - | - | -
Milestone 1 |  | 2022-02-10 | 2022-02-27
Story plot/theme and character setting | Alex | 2022-02-10 | 2022-02-27 | 0 | 0% | bar: WEEK 1 F to WEEK 2 T; WEEK 5 M to WEEK 9 F
GUI (health bar, sanity bar) | Jason |  | 2022-02-27 | 43977 | 20% | bar: WEEK 2 W; WEEK 5 M to WEEK 9 F
Level design (Basic planning: Big picture) | Edeline, Alex, Thang | 2022-02-14 | 2022-02-20 | 6 | 5% | bar: WEEK 2 W; WEEK 5 M to WEEK 9 F
Level assets polygon design (Theme, assets, objects, physics & mechanics — To test placing them in a level) | Edeline, Alex | 2022-02-21 | 2022-02-27 | 6 | 0% | bar: WEEK 2 W to WEEK 3 W; WEEK 5 M to WEEK 9 F
Basic actions (Walking, dash/dodge, block) | Tian Fang, Zhu Bo | 2022-02-14 | 2022-02-27 | 13 | 0% | bar: WEEK 3 M to WEEK 3 R; WEEK 5 M to WEEK 9 F
Basic actions ( 1 type of enemy — To test damage, how enemies react) | Tian Fang, Zhu Bo | 2022-02-14 | 2022-02-27 | 13 | 0% | bar: WEEK 3 T to WEEK 3 R; WEEK 5 M to WEEK 9 F
Aesthetics - Art, music, sound effects (can decide after actions) | Edeline, Tian Fang (for sound and music), extra helper if possible |  | 2022-02-27 | 43977 | 0% | bar: WEEK 3 F; WEEK 5 M to WEEK 9 F
Level implementation (Basic flat floor, rect platform) | Jason, Alex |  | 2022-02-27 |  | 0% | bar: WEEK 2 W to WEEK 3 W; WEEK 5 M to WEEK 9 F
Milestone 2 |  | 2022-02-28 | 2022-03-20
Strategic actions (Abilities) |  |  |  | 0 | 0% | bar: WEEK 4 M to WEEK 4 R; WEEK 5 M to WEEK 9 F
Strategic actions (Attack damage numbers (how much of enemies’ health)) |  |  |  | 0 | 0% | bar: WEEK 4 F to WEEK 9 F
Enemy design (More types of enemies, attack style etc) |  |  |  | 0 | 0% | bar: WEEK 3 T to WEEK 3 R; WEEK 5 M to WEEK 9 F
Level design (Create the levels) |  |  |  |  | 0% | bar: WEEK 4 F to WEEK 9 F
Level design (Advanced planning: puzzle concepts) |  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
Level design (Advanced planning: Location of enemy) |  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
Level implementation (Puzzles & enemy locations) |  |  |  |  | 0% | bar: WEEK 5 M to WEEK 9 F
Enemy design & AI (Balancing) |  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F
|  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 9 F